## Sheet1
kAI Project Plan

	Time allowed	Time allocated	Predicted time allocated	Time Remaining			Current average weight:	0.9018518519
Sprint 1 (29/03 – 01/04)	26	20.75	19.1643518519	8.35
Task		Predicted Time	Weighted predicted time	Actual Time	Ratio	Started	End
Initial Project setup		3	2.7055555556	3	1
KAIObject (initial data)		1.5	1.3527777778	1	0.6666666667
kAIPort (initial data)		0.75	0.6763888889	0.75	1	15:20:00
kAINode (initial data)		2	1.8037037037	2	1	18:25:00	19:40:00	20:52:00	21:30:00
kAIAction (initial data)		3	2.7055555556	0.7	0.2333333333	22:35:00	23:00:00	01:10:00	01:25:00
KAIInput (initial data)		3	2.7055555556	1.25	0.4166666667	11:50:00	13:05:00
kAITrigger (initial data)		1.5	1.3527777778	0.7	0.4666666667	00:40:00	01:05:00
kAIBehaviour (initial data)		3	2.7055555556		1
kAIPort refactor – connect to multiple things		1.5	1.3527777778	2	1.3333333333	16:00:00	16:47:00	17:45:00	19:00:00
kAIConstant (initial data)		1	0.9018518519		1
Initial GUI Design		0.5	0.9018518519	1	2
			0		1
			0		1
			0		1
			0		1	13:15:00	13:40:00
			0		1
			0		1
			0		1
			0		1
	Time allowed	Time allocated	Predicted time allocated
Sprint 2 (15/04 – 29/04)	16	5.5	4.9601851852
		Predicted Time	Weighted predicted time	Actual Time	Ratio
kIAPort Test		1	0.9018518519		1
kIANode Test		1.5	1.3527777778		1
kAIAction Test		1	0.9018518519		1
kAIInpput Test		2	1.8037037037		1
			0		1
			0		1
			0		1
			0		1
			0		1
			0		1
			0		1
			0		1
			0		1
			0		1
			0		1
			0		1
			0		1

## Sheet2
Sprints

Sprint 1