## Sheet1
kAI Project Plan

	Time allowed	Time allocated	Predicted time allocated				Current average weight:	1
Sprint 1 (01/04 – 14/04)	23	16.75	16.75
Task		Predicted Time	Weighted predicted time	Actual Time	Ratio
KAIObject (initial data)		1.5	1.5		0
kAIPort (initial data)		0.75	0.75		0
kAIConnexion (initial data)		2	2		0
kAINode (initial data)		2	2		0
kAIAction (initial data)		3	3		0
kAIInpit (initial data)		3	3		0
kAITrigger (initial data)		1.5	1.5		0
kAIBehaviour (initial data)		3	3		0

	Time allowed	Time allocated	Predicted time allocated
Sprint 2 (15/04 – 29/04)	16	0	0
		Predicted Time	Weighted predicted time	Actual Time	Ratio

## Sheet2
Sprints

Sprint 1