## Sheet1
kAI Project Plan					Current average weight:
				0.90
	Time allowed	Time allocated	Predicted time allocated			Time Remaining	Predicted time remaining
Sprint 1 (29/03 – 01/04)	26.00	28.59	26.28			9.84	8.89
Task		Predicted Time	Weighted predicted time	Actual Time	Ratio	Started	End
Initial Project setup		3.00	2.71	3.00	1.00
KAIObject (initial data)		1.50	1.36	1.00	0.67
kAIPort (initial data)		0.75	0.68	0.75	1.00
kAINode (initial data)		2.00	1.81	2.00	1.00
kAIAction (initial data)		3.00	2.71	0.70	0.23
KAIInput (initial data)		3.00	2.71	1.25	0.42
kAITrigger (initial data)		1.50	1.36	0.70	0.47
kAIBehaviour (initial data)		3.00	2.71		1.00
kAIPort refactor – connect to multiple things		1.50	1.36	2.25	1.50	20:00:00
kAIConstant (initial data)		1.00	0.90		1.00
Initial GUI Design		0.50	0.90	1.00	2.00
GUI Initial Setup		0.50	0.45		1.00
Menu bar		0.34	0.31		1.00
Action and Behaviour dictionaries		0.75	0.68		1.00
Selection bar		1.00	0.90		1.00
Node		1.00	0.90		1.00
Working out different types of AI		2.00	1.81	1.50	0.75	16:10:00	16:20:00	17:20:00	18:10:00	19:40:00	20:00:00
Action Node		0.75	0.68		1.00
Port		1.50	1.36		1.00
	Time allowed	Time allocated	Predicted time allocated			Time Remaining	Predicted time remaining
Sprint 2 (2/04 – 11/04)	14.00	14.00	12.65			14.00	12.65
		Predicted Time	Weighted predicted time	Actual Time	Ratio
kIAPort Test		1.00	0.90		1.00
kIANode Test		1.50	1.36		1.00
kAIAction Test		1.00	0.90		1.00
kAIInpput Test		2.00	1.81		1.00
kAITrigger Tests		1.50	1.36		1.00
Input Port (GUI)		1.00	0.90		1.00
Trigger Port (GUI)		1.00	0.90		1.00
Behaviour Node		0.75	0.68		1.00
Properties window initial		0.75	0.68		1.00
Properties window behaviour		1.50	1.36		1.00
Port connexion		2.00	1.81		1.00
	Time allowed	Time allocated	Predicted time allocated
Sprint 3 (15/04 – 26/04)	16.00	16.00	14.45
kAIBehaviour Test		2.00	1.81		1.00
Properties inputs		1.00	0.90		1.00
Properties triggers		1.00	0.90		1.00
XML First pass		2.00	1.81		1.00
kAIPort XML		2.00	1.81		1.00
kAINode XML		2.00	1.81		1.00
kAIPort XML Test		2.00	1.81		1.00
kAINode Xml Test		2.00	1.81		1.00
Solution class		2.00	1.81		1.00

## Sheet2
Sprints
Task	Estimated time
Sprint 1 (kAIBehaviour)	6
Public interface	1
Port methods	2
Sub behaviour methods	2