## Sheet1
kAI Project Plan

	Time allowed	Time allocated	Predicted time allocated				Current average weight:	0.9761904762
Sprint 1 (01/04 – 14/04)	44	21.75	21.2321428571
Task		Predicted Time	Weighted predicted time	Actual Time	Ratio	Started	End
Initial Project setup		3	2.9285714286	3	1
KAIObject (initial data)		1.5	1.4642857143	1	0.6666666667
kAIPort (initial data)		0.75	0.7321428571	0.75	1	15:20:00
kAINode (initial data)		2	1.9523809524	2	1	18:25:00	19:40:00	20:52:00	21:30:00
kAIAction (initial data)		3	2.9285714286		1	22:35:00	23:00:00
KAIInput (initial data)		3	2.9285714286		1
kAITrigger (initial data)		1.5	1.4642857143		1
kAIBehaviour (initial data)		3	2.9285714286		1
kAIPort refactor – connect to multiple things		1.5	1.4642857143		1
kAIPort refactor – only store connexions in one direction		1.5	1.4642857143		1
kAIConstant (initial data)		1	0.9761904762		1
			0		1
			0		1
			0		1
	Time allowed	Time allocated	Predicted time allocated
Sprint 2 (15/04 – 29/04)	16	0	0
		Predicted Time	Weighted predicted time	Actual Time	Ratio

## Sheet2
Sprints

Sprint 1