## Sheet1
kAI Project Plan

	Time allowed	Time allocated	Predicted time allocated				Current average weight:	0.8833333333
Sprint 1 (01/04 – 14/04)	44	21.75	19.2125
Task		Predicted Time	Weighted predicted time	Actual Time	Ratio	Started	End
Initial Project setup		3	2.65	3	1
KAIObject (initial data)		1.5	1.325	1	0.6666666667
kAIPort (initial data)		0.75	0.6625	0.75	1	15:20:00
kAINode (initial data)		2	1.7666666667	2	1	18:25:00	19:40:00	20:52:00	21:30:00
kAIAction (initial data)		3	2.65	0.7	0.2333333333	22:35:00	23:00:00	01:10:00	01:25:00
KAIInput (initial data)		3	2.65		1
kAITrigger (initial data)		1.5	1.325	0.7	0.4666666667	00:40:00	01:05:00
kAIBehaviour (initial data)		3	2.65		1
kAIPort refactor – connect to multiple things		1.5	1.325		1
kAIPort refactor – only store connexions in one direction		1.5	1.325		1
kAIConstant (initial data)		1	0.8833333333		1
			0		1
			0		1
			0		1
	Time allowed	Time allocated	Predicted time allocated
Sprint 2 (15/04 – 29/04)	16	0	0
		Predicted Time	Weighted predicted time	Actual Time	Ratio

## Sheet2
Sprints

Sprint 1