## Sheet1
kAI Project Plan

	Time allowed	Time allocated	Predicted time allocated				Current average weight:	0.8416666667
Sprint 1 (01/04 – 14/04)	44	21.75	18.30625
Task		Predicted Time	Weighted predicted time	Actual Time	Ratio	Started	End
Initial Project setup		3	2.525	3	1
KAIObject (initial data)		1.5	1.2625	1	0.6666666667
kAIPort (initial data)		0.75	0.63125	0.75	1	15:20:00
kAINode (initial data)		2	1.6833333333	2	1	18:25:00	19:40:00	20:52:00	21:30:00
kAIAction (initial data)		3	2.525	0.7	0.2333333333	22:35:00	23:00:00	01:10:00	01:25:00
KAIInput (initial data)		3	2.525	1.25	0.4166666667	11:50:00	13:05:00
kAITrigger (initial data)		1.5	1.2625	0.7	0.4666666667	00:40:00	01:05:00
kAIBehaviour (initial data)		3	2.525		1
kAIPort refactor – connect to multiple things		1.5	1.2625		1
kAIPort refactor – only store connexions in one direction		1.5	1.2625		1
kAIConstant (initial data)		1	0.8416666667		1
			0		1
			0		1
			0		1
	Time allowed	Time allocated	Predicted time allocated
Sprint 2 (15/04 – 29/04)	16	0	0
		Predicted Time	Weighted predicted time	Actual Time	Ratio

## Sheet2
Sprints

Sprint 1